# Hotel Reservation System

Six Week Role Responsibilities and Detailed Plan

COMPSCI 557 | Group 7 | Team working document

This document replaces the earlier role-detail draft for day-to-day implementation. It aligns the five roles, Java web stack, database interfaces, booking rules, and handoffs with the current repository baseline. Start from the GitHub README and treat docs/PROJECT_RULES.md as the implementation contract.

# Repository and source of truth

Repository: https://github.com/Jaewon-seong-git/CS-557-Group7

Implementation contract: docs/PROJECT_RULES.md

Java 17, Jakarta Servlet 6.0, Tomcat 10.1, MySQL 8.0+, JDBC, JSP under WEB-INF/views, HTML/CSS/JavaScript. Do not use Flask or Python for the web application.

If an instructor rubric conflicts with a technical rule, confirm the rubric and update PROJECT_RULES.md before changing code.

# Schedule note

The earlier documents disagree on dates: the detailed file names a Nov 12 intermediate deadline and Dec 15 demo, while the proposal lists Dec 22 as the demo date. The six-week build plan runs through Dec 6 and treats course dates as requiring confirmation. Confirm official dates before putting them in a submission email. Earlier Phase 1 references also differ between Nov 8 and Nov 9; this plan uses Nov 9 as the internal integration checkpoint.

# Six week schedule at a glance

| Week | Dates | Shared checkpoint |
| --- | --- | --- |
| 1 | Oct 26-Nov 1 | Confirm interfaces; schema/DAO skeletons and runnable setup |
| 2 | Nov 2-Nov 8 | DB schema v1, common Java helpers, JSP/Servlet skeletons |
| 3 | Nov 9-Nov 15 | Phase 1 integration checkpoint by Nov 9; prepare interim evidence |
| 4 | Nov 16-Nov 22 | Guest booking and Admin approval connected end to end |
| 5 | Nov 23-Nov 29 | Payment, cancellation, expiry and Admin tools; integration fixes |
| 6 | Nov 30-Dec 6 | Boundary/security checks, clean setup, code freeze candidate and demo rehearsal |

# Shared implementation rules

| Area | Agreed implementation |
| --- | --- |
| Tables | User, RoomType, Room, Reservation, Payment. RoomType owns capacity and nightly price; Room is physical inventory. |
| Reservation status | PENDING -> APPROVED -> CONFIRMED; cancellation/expiry -> CANCELLED. PENDING, APPROVED and CONFIRMED block a room. |
| Payment | Payment is allowed only after approval and at least 7 calendar days before check-in. Successful payment changes Reservation to CONFIRMED. |
| Booking window | Check-in must be at least 7 calendar days away. UI wording: “at least 7 days before check-in”; remove the old 8-day rule. |
| Cancellation | Before check-in: unpaid has no refund; paid reservation refund is >7 days: 100%, 3-7 days inclusive: 50%, 1-2 days: 0%. Reject on/after check-in. |
| Expiry | Admin action calls sp_expire_overdue; unpaid PENDING/APPROVED reservations with fewer than 7 days become CANCELLED. |
| Overlap | Stays are [check_in, check_out). Overlap iff existing.check_in < requested.check_out AND existing.check_out > requested.check_in. Enforce in procedure and BEFORE INSERT trigger. |
| Schema additions | Reservation.total_price snapshots the quote. Payment.payment_status is PAID, PARTIALLY_REFUNDED, REFUNDED or VOID. Role 2 includes both. |
| Security | Use PreparedStatement. Derive guest_id and role from session. Never trust browser guest_id, price, refund amount or role. |
| Git | Use a branch and PR; name interface changes; keep secrets and actual context.xml out of Git. |

## Course database constructs

Two triggers: Reservation overlap/date guard; Payment eligibility guard and Reservation status transition.

Three procedures: sp_create_reservation, sp_cancel_reservation, sp_expire_overdue. The expiry procedure contains the required cursor.

Two views, two composite indexes, Admin/Guest database accounts with least privilege, ERD, constraints, sample data and SQL boundary evidence.

# Role 1 | Project Management and Java Integration

Owner: Jaewon Seong    Review partner: Role 4

Own the common Java foundation and integration contract. Coordinate work and keep repository rules, DAO interfaces and shared implementation documentation consistent.

## Owned work and files

GitHub branches/PR guidance, Jira, meeting and hours logs, weekly status and workload review.

Java web skeleton, JNDI connection pools, PreparedStatement helpers, validation, PBKDF2 hashing, registration/login/logout, sessions and RoleFilter/RBAC.

DAO files: DBConnection.java, UserDAO.java, RoomDAO.java, ReservationDAO.java; keep mappings aligned with PROJECT_RULES.md.

Coordinate DAO/Servlet handoffs; review integration and security; assemble reports, contribution table, slides and demo.

## Six week plan

| Week | Tasks | Deliverable / handoff |
| --- | --- | --- |
| 1 | Publish repo instructions and interface contract; confirm project runs; agree branch/PR and Jira workflow. | README/Jira; runnable shell; owners recorded. |
| 2 | Complete connection/configuration, validation, PBKDF2 and DAO contracts; support schema alignment. | Common helpers v1 and DAO method list. |
| 3 | Finish registration/login/logout, session attributes and RoleFilter; integrate routes. | Phase 1 checkpoint: auth/DAO foundation compiles; routes documented. |
| 4 | Connect DAO to SQL/procedures; lead login > search > request > approve checkpoint. | Core flow and integration notes. |
| 5 | Connect payment/cancel/expiry/admin flows; resolve mismatches; update README. | Critical flows integrated; setup guide current. |
| 6 | Run session tampering, validation and SQL injection checks; collect report inputs and rehearse. | Security checklist and release candidate. |

# Role 2 | Database Construction

Owner: Grant Ross    Review partner: Role 3

Own the relational schema and reproducible setup. Coordinate names, columns and keys with DAO and procedure owners before freezing DDL.

## Owned work and files

ERD in Chen notation and five-table schema with PK/FK/UNIQUE/NOT NULL/CHECK constraints.

Include Reservation.total_price and Payment.payment_status; keep room capacity and rate in RoomType.

Create indexes, Available_Rooms_View, Active_Guest_Summary_View, least-privilege DB accounts, hash-only seed data.

Supply DTO beans, fresh-database setup script and schema notes. Preserve booking history when deleting users/rooms.

## Six week plan

| Week | Tasks | Deliverable / handoff |
| --- | --- | --- |
| 1 | Extract entities; draft ERD; agree columns/types with Roles 1 and 3. | ERD v1; interface questions resolved. |
| 2 | Finish five-table DDL v1 including both schema additions; test in MySQL. | DDL v1 and ERD v2. |
| 3 | Add constraints/indexes/views and data for each status. | Schema, views, indexes, representative seed data. |
| 4 | Create Admin/Guest accounts and grants; generate DTOs; verify DAO queries. | DB setup script and DTOs. |
| 5 | Test referential behavior, room deletion with history and view output; record changes. | Schema change log and report evidence. |
| 6 | Run setup from a clean DB; finalize ERD/schema slides and report section. | Clean-install SQL and final DB artifacts. |

# Role 3 | Database Programming

Owner: J Jesus Flores-Rios    Review partner: Role 2

Own database-side business logic. Publish exact callable interfaces and error cases before UI integration.

## Owned work and files

Document lifecycle, overlap, 7-day booking/payment/expiry cutoff, refund tiers and boundaries.

Publish procedure signatures, inputs/outputs, UI query contract and error behavior.

Implement two triggers, three procedures, expiry cursor, transaction/error handling and SQL tests.

Keep transaction ownership in stored procedures and align statuses with the shared contract.

## Six week plan

| Week | Tasks | Deliverable / handoff |
| --- | --- | --- |
| 1 | Write rules/interface table; confirm status fields and cutoffs with Roles 1/2. | Rules and procedure signatures. |
| 2 | Implement search/admin/user queries; settle overlap and expiry behavior. | Query examples and SQL contract. |
| 3 | Implement sp_create_reservation with room lock, overlap check, price snapshot, PENDING insert; add overlap trigger. | Create routine and overlap evidence. |
| 4 | Implement payment trigger and sp_cancel_reservation; test >7, 7, 3, 2 and 1-day cases. | Payment/cancel logic and boundary evidence. |
| 5 | Implement sp_expire_overdue cursor and safe repeat runs; verify cutoff. | Expiry routine and cursor evidence. |
| 6 | Run DB/app integration scenarios; finalize SQL and screenshots. | SQL routines/triggers and test evidence. |

# Role 4 | Admin Web UI

Owner: Techin Wasakul    Review partner: Role 5

Own Admin JSP/Servlet workflows. Use the shared authentication foundation and server-side Admin authorization.

## Owned work and files

JSP views under WEB-INF/views and Admin dashboard, room CRUD, RoomType pricing, reservations, guest directory and expiry action.

Approve only PENDING -> APPROVED; implement constrained status overrides preserving valid states/refunds.

Show validation and DB errors; never expose password hashes.

Do not duplicate LoginServlet/session implementation; coordinate login view with Role 1.

## Six week plan

| Week | Tasks | Deliverable / handoff |
| --- | --- | --- |
| 1 | Map Admin pages, routes, forms and DAO calls. | Admin route/page contract. |
| 2 | Build Admin JSP layout with placeholder data; connect login redirect/filter contract. | Admin skeleton. |
| 3 | Implement room CRUD and RoomType price update. | Inventory/pricing flow. |
| 4 | Implement reservation queue and approval action. | PENDING -> APPROVED; integrated checkpoint. |
| 5 | Add guest directory, status override, expiry action and DB errors. | Admin tools connected to DB. |
| 6 | Test Admin-only access, validation and status transitions; prepare demo. | Admin checklist/screenshots/demo. |

# Role 5 | Guest Web UI

Owner: Hudayfa A Sharif    Review partner: Role 4

Own Guest JSP/Servlet workflows. Derive guest identity from session and check ownership for every booking action.

## Owned work and files

Guest dashboard, date/type search, reservation, My Bookings, payment, cancellation and own profile. Registration view uses Role 1 endpoint.

Show server quote and current price; display clear 7-day cutoff messages.

Pay only eligible APPROVED booking; display server-calculated refund; do not trust submitted guest_id/price/refund.

Test URL/ID tampering and access to another guest’s records.

## Six week plan

| Week | Tasks | Deliverable / handoff |
| --- | --- | --- |
| 1 | Map pages, routes, forms and error states with Roles 1/3. | Guest route/page contract. |
| 2 | Build JSP layout and search mockup; connect session contract. | Guest skeleton. |
| 3 | Implement profile and real search; show type/capacity/price; validate dates. | Profile and available-room search. |
| 4 | Implement reservation and My Bookings using DAO/procedure contract. | Reservation request and bookings. |
| 5 | Implement Pay/Cancel actions and server-side ownership checks. | Payment/cancellation connected. |
| 6 | Test date boundaries, access, ID tampering and error handling; prepare demo. | Guest checklist/screenshots/demo. |

# Required handoffs and integration gates

| Gate | Required handoff | Acceptance check |
| --- | --- | --- |
| End Week 1 | Role 2 schema draft, Role 3 interface, UI routes/forms, Role 1 shared contract. | No conflicting table/status/date/path/procedure names. |
| End Week 2 | Common helpers, DDL v1, query contract and UI skeletons. | Project imports/runs; sample database connects. |
| Nov 9 internal checkpoint | Phase 1 files committed and integrated. | Build succeeds; no credentials committed; blockers have owners. |
| End Week 4 | Search -> request -> Admin approve on real DB. | Overlap rejected; quote shown; guest ID from session. |
| End Week 5 | Payment, cancel/refund, expiry and Admin tools. | DB routines own state and money calculations. |
| End Week 6 | Clean setup, boundary/security evidence, demo and code freeze candidate. | README setup works on clean environment; bugs tracked. |

# Team operating rules

Each member records actual hours weekly and posts a Jira update. Target is 3-5 hours/member/week; review workload every two weeks.

Use own branches and PRs. Roles 2/3 review SQL; Roles 4/5 review UI; Role 1 reviews shared Java/interfaces.

Every PR states changes, run steps, interface changes and evidence. Update PROJECT_RULES.md when a shared contract changes.

Each person prepares contribution notes, screenshots and slide content; PM assembles and checks consistency. Raise blockers with dependency and needed-by date.

Reserve Dec 7-22 for final report/slides/demo only if the instructor confirms that schedule; otherwise use the official course deadline.